Terms of Reference

Health and Education Assessment

SOS Children’s Villages Viet Nam

- BACKGROUND

SOS Children’s Villages International is a child-centred development organization working across 135 countries of the world, without religious, political or governmental affiliations, working towards the provision of family based alternative care and strengthening families for the children who are deprived of parental care or at the risk of losing parental care in near future. SOS Children’s Villages International’s 2030 Strategy primarily focused on seven broad key areas to ensure innovative and creative approaches in order to achieve sustainable goals through practical measures such as:

- Innovative Alternative Child Care

- Strengthen Families through community based Programmes

- Empower Youth Groups

- Advocate for Children

- Create a Social Movements about the Safety and Security of Children

- Simplify SOS Systems

- Invest for Funding Growth etc.

These strategic initiatives will ensure an environment where a child will grow with proper parental care in order to realise their full potential in future at the same time these will enable SOS Children’s Villages International to focus and engage with only relevant work align those services that are no longer needed due to considerable developmental works done by government and other stakeholders over a period of time. On this, SOS Children’s Villages International federation had taken a constructive and time-tested decision to focus only on core programme and the rest will be aligned with specific need of local community through an assessment exercise especially in the areas of Health and Education (H&E) Programmes across Asia Region.

2. Main Objectives

The primary objectives of such exercise are:

- To ensure to programme are relevant to the need of the poorest of the poor

- To ensure innovative and cost-effectiveness of programme

- To ensure the sustainability of programme

- To ensure sustainable development goals in league with Government and other recognized stakeholders for strong impact on the target group of children.

3.Scope of Work:

The scope of work is primarily deals with range and reach of services that are being provided under Health and Education Projects based the missionary goals of the SOS Children’s Villages International:

- Identification of target group of children in HGS and assess the levels of vulnerability as per the SOS Mission

- Mapping range and reach of similar services provided by Government and other stakeholders within the locality

- Assess who is best placed service providers; Government or other stakeholders in the local area in terms of the capacity to provide long term quality education, training and health care services to the target group of children

- Identification of target group of children in Health Care Centre and assess the levels of vulnerability as per the SOS Mission

- Mapping range and reach of similar services provided by Government and stakeholders within the locality

- Assess the collaboration, joint activities between SOS Children’s Villages, government bodies and other stakeholders in implementation of health and education projects

- A detail assessment about the stakeholders based on three basic criteria: financial self-sufficiency, capacity to provide high quality services and long term commitments to cater the need of the target group of children

- National Training Centres (NTCs) and Vocational Training Centres (VTCs) are also need to be incorporated under this assessment exercise

- Cases of closure along with handover, collaboration with government and other stakeholders are need to be assessed and the possible risks for the same will also need to be analysed with evidence based recommendations for practical resolution.

- Study the guidelines and policies of the Party, the policies and legislation of the State with regard to educational and health facilities in Viet Nam towards 2030 to identify type of school amongst existing SOS educational facilities.

Thus the assessment ultimately will pave the way for taking decisive decisions in regard to closure, alignment and meaningful partnerships with eligible and competent stakeholders and organisations by December 2019. In the process MAs, as key agents of change will take the primary responsibility and PSAs and General Secretariat and IO will provide strategic advice in organizing and managing the entire exercise.

In Viet Nam, facilities to be assessed are:

- 12 Hermann Gmeiner School, including:

+ 10 schools of 3 general education levels in Ha Noi, Ho Chi Minh City, Hai Phong, Da Nang, Viet Tri/Phu Tho, Vinh/Nghe An, Nha Trang/Khanh Hoa, Da Lat/Lam Dong, Ben Tre and Ca Mau;

+ 01 school with 2 general education level, i.e. primary and lower secondary, in Dien Bien Phu/Dien Bien

+ 01 school with primary level only in Thanh Hoa.

- 04 vocational training facilities, including:

+ 01 Hermann Gmeiner Vocational Training School in Viet Tri, Phu Tho

+ 03 vocational training workshop in Ben Tre, Nha Trang, Da Nang

- 01 health care facility in Da Lat.

- 01 facility for internal training to SOS staff in Ha Noi.

4. Key questions need to be addressed through H&E Assessment:

- Whether SOS educational, training and health facilitiesare reaching out to relevant target group of children minimum 30% out of total beneficiaries (including FBC and FSP) both in a school or not, at present and in coming 5 years.

- Who is the best placed (SOS, Government or other competent and recognized stakeholders) to provide the service in terms of accessibility, affordability and quality education, training and health care services

- Whether the MA (Member Association) is self-sufficient financially and reaching out minimum/acceptable number of children from the target group. Whether SOS educational, training and health care services are good enough to the target children. in the local area?

- Whether SOS educational, training and health facilities can be self-sufficient financially to manage the entire cost of the health care programme.

5. Components of the Study

Secondary Research: This will consist of literature review of existing studies, programmes, reports and key policy and strategy documents to understand about SOS mission, vision, approaches, key functional areas, planning processes. The research will include review of governmental legislations, programmes and projects.

Primary Research: This will deal with direct interview with relevant stakeholders in order to assess the above questions.

6. Methodology of the Proposed Study:

SOS Children’s Villages International seeks to undertake the assessment through two key components:

- Qualitative Research: This will consists of Case Study of significant and innovative programmes as per the guidance of IO-Asia

- Quantitative Research: Undertake a quantitative research consists of interview for the relevant stakeholders in consultation with MA.

7. Timeline:

The data collection and first phase of data entry are expected to be completed by two months from the date of commissioning of research agency.

8. Major Deliverables:

- Develop Inception Report followed by first meeting with the MA

- Develop Research design in consultation / guidance of IO-Asia

- Develop field work schedule as per the requirement in consultation with MA

- Develop and share brief narrative report apart from data entry into the official template and incorporation of comments from MA and GSC

- Present final report of international standards that will include cost-benefit analysis, detail risk analysis and feasible resolution of the same and evidence based recommendations in consultation with IO-Asia

- Preparation of PPT of the main findings of the assessment

- Share PDF version and word version of print ready final file

- Conduct dissemination workshop with key stakeholders in consultation with IO-Asia

9. Expected profile of the Consultant/Agency:

- A person/s or research agency with excellent knowledge and robust experience in the areas of education and health programs of development sector and outstanding report writing skills

- A person/s or research agency is expected to be competent in personnel management and field management skills to organise large scale assessment of development sector

- A person/s or research agency is expected to be well-versed in data analysis and report writing skills

- A person/s or research agency is expected to work independently without regular supervision and micro-management from SOS

- Respect mutually agreed time line at each stage all through the processes as per mutually agreed work plan

- Person with ability to handle issues of sensitivity while dealing with children, youth and all other beneficiaries in the field.

10. Terms of Payment:

- First instalment of 25% will be paid after receiving Inception Report

- Second instalment of 25% will be paid after the submission of detail work plan and schedule

- Third instalment of 20% will be paid after the submission of Draft Report

- Fourth and final instalment of 30% will only be paid after the submission of satisfactory final report, incorporating all comments along with all soft and hard copies of documents and reports collected from SOS, data-base sheet in all formats, audio-video records, transcripts, PPT on final report and the completion of dissemination workshop based on the key findings of the assessment.

All payments are linked to specific deliverable as per the existing policies of SOS Children’s Villages International and no payments will be made without satisfactory deliverable/s by the agency.

11. Compliance with SOS Children’s Villages Child protection Policy and Code of Conduct

This assignment may require the agency/ consultant/s to sign and adhere to SOS Children’s Villages International Child Safeguarding / Child Protection Policy and Code of Conduct which are mandatory.

12. Confidentiality

A person/s or research agency shall not disclose the results of the research by any means of media, shall not share data, reports of the research to any third parties without the consent of SOS Children’s Villages Viet Nam.

13. Requirements on bidding:

a) Competencies profile of a person/s research agenecy

b) Reports of researches that are complete or in progress from 2012 till now (at least 3 researches)

c) Proposal for SOS Health and Education Assessment

14. Deadline for Proposal:

The last date for submission of proposal along with detail budget with cost of unit price, latest three sample reports by 05th March and the proposal may be submitted at the email ID: ductho@sosvietnam.org Only selected agencies will be called for first round of interview.

# Text boxes

National Office

Alley 1, Pham Van Dong Street,

Mai Dich Ward,

Cau Giay District,

Hanoi City, Vietnam;

Tel: +84 4 37644019/

+84 4 37641229/

+84 4 37641223;

Fax: + 84 4 37644020;

Email: office@sosvietnam.org; www.sos-childrensvillages.org